## Sheet1
Business Requirement | Description | Process or form requried? | Action | Required by Decision or Implementation? | Decision | Implementation
1 | Ability for parties to request data | No | Amend BSC to reflect | Decision
1.1 | BSCCo to provide data request form | Yes | Create data request form - include overview/template/ highlevel in Consultation | Implementation
1.2 | BSCCo to conduct critical friend analysis | No | Add to BSC/BSCP | Decision
1.3 | Data request form to be easily accessible | No | Idntify location on website | Implementation
1.4 | Instructions for data request form | Yes | Create instructions alongside creting form | Implementation
1.5 | Data request form shall highlight mandatory and optional areas | Yes | Make clear on form | Implementation
1.6 | BSCCo shall have a single point of contact for receiving requests | No | Determine which team will run the Data process | Decision
1.7 | Establish process for acknowledging request | Yes | Create Process | Decision
2 | Identify teams / individual to triage data request | Yes | Process for assigining triage | Decision
2.1 | BSCCo to publish document detailing triage process | Yes | Draft process document | Implementation
2.2 | BSCCo to establish processes for updating open data documents | Yes | Include with 2.1 process document | Decision
2.3 | BSCCo to establish Local Working Instructions (LWI) for processing data requests | Yes | Write LWIs | Implementation
3 | BSCCo to consider mitigation methods | No | Add to BSC/BSCP | Decision
3.1 | BSCCo to publish document detailing mitigation methods. | Yes | Include in BR2.1 | Implementation
4 | BSCCo to classify data | No | Add to BSC/BSCP | Decision
4.1 | BSCCo to publish document detailing data classification. | No | Include in BR2.1 | Implementation
5 | BSCCo to assess time and effort required for data request | No | Add to LWI in BR2.3 | Decision
5.1 | BSCCo to request input from BSC Agents | Yes | Process for requesting BSC Agent Data | Decision
5.1 | BSCCo to request input from BSC Agents | No | CRs to SPs for SPIA | Decision
5.2 | BSCCo to assess costs | Yes | Process for assesing costs | Decision
5.3 | BSCCo to assess effort | Yes | Process for assesing effort | Decision
5.4 | BSCCo to consider the benefits of data request | Yes | Add to LWI in BR2.3 | Implementation
5.5 | BSCCo to consider the impacts to wider industry. | Yes | Add to LWI in BR2.3 | Implementation
6 | BSCCo to make recommendation to BCB. | No | Add to BSC/BSCP | Decision
7 | BSCCo to consult industry on recommendation | No | Add to BSC/BSCP | Decision
7.1 | Template for consultation | Yes | Create Consultation template | Implementation
7.2 | Template for responses | Yes | Create Consultation template | Implementation
7.3 | Instructions for response form | Yes | Include in templates | Implementation
8 | BSCCo to present recommendation to BCB | No | Add to BSC/BSCP | Decision
8.1 | Template for presenting recommendation | Yes | Create template | Implementation
9 | BCB to make decision on data request | No | Add to BSC/BSCP | Decision
10 | BSCCo Standing Delegation | No | Add to BSC/BSCP | Decision
10.1 | Standing Delegation Process | Yes | Add to BSC/BSCP | Decision
10.2 | List of Delegations to be Public | Yes | Create process for Publishing delegation, inc. location | Decision
10.3 | List of Delegations to be reviewed | No | Add review Periodicity to BSC/BSCP | Implementation
11 | BCB to notify requesting party of decision | No | Add to BSC/BSCP | Decision
|  | No | Identify how mail list will be formed | Implementation
12 | Terms of Reference for BCB | No | Add of BSC/BSCP | Decision
12.1 | BSCCo to Publish BCB TOR | No | Consider if better to be encoded or stand-alone. If Stand-alone - where? | Decision
13 | BSCCo shall publish approved data sets in electronic format | No | Add to BSC/BSCP | Decision
13.1 | Published data sets must be discoverable | Yes | Process for Piublishing and identify location for publishing - tie in with 10.2, 12.1, and 13.0 | Implementation
13.2 | Published data sets must be descriptive | No | Identify what needs to be in despcriptiosn - create template | Implementation
13.3 | BSCCo shall publish all data requests and outcomes | Yes | Tie in with 10.2, 12.1, 13.0 and 13.1 | Implementation
13.4 | BSCCo shall publish circular and notice | Yes | Design circular template/identify existing circular to use - if solatter, consider standard format | Implementation
13.5 | Details of requests can remain anonymous | Yes | Tie-in with BR1 - ensure BR1.1 outcomes make clear that anonymity is available | Implementation
14 | Requesting party shall have ability to appeal a decision | No | Add to BSC/BSCP | Decision
14.1 | Appeals process | Yes | Create process | Decision
14.2 | BSCCo to provide appeal form | Yes | Design form | Implementation
14.3 | BSCCo to publish document detailing appeals process | No | Create guidance/Instruction form | Implementation
14.4 | Panel to review appeal and make decision | No | Add to BSC/BSCP | Decision
14.5 | Panel to notify appealing party of outcome | No | Add to BSC/BSCP | Decision
15 | BSCCo to submit report to Ofgem | No | Dsicsuss content and periodicity with Ofgem | Implementation